## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Organize/Planning | 1 | 4 | 1 | 10 | 100%
First Meeting | 2 | 1 | 2 | 1 | 100%
Read over project specs | 2 | 3 | 2 | 9 | 100%
Create Group Database | 2 | 1 | 2 | 2 | 100%
Second Meeting | 3 | 1 | 3 | 1 | 100%
Assign Tasks | 3 | 1 | 3 | 8 | 100%
Work on individual tasks | 3 | 5 | 4 | 7 | 100%
Third Meeting | 4 | 1 | 4 | 1 | 100%
Group Assigned Tasks | 6 | 4 | 6 | 5 | 100%
Fourth Meeting | 7 | 1 | 7 | 1 | 100%
Individual/group assigned tasks | 7 | 3 | 7 | 4 | 100%
Fifth Meeting | 8 | 1 | 8 | 1 | 100%
Work on individual/group tasks | 8 | 2 | 8 | 3 | 90%
Sixth Meeting | 10 | 1 | 10 | 1 | 100%
PowerPoint Presentation | 6 | 2 | 9 | 2 | 100%
Voice Annotations | 6 | 2 | 9 | 2 | 100%
Create Project 2 | 7 | 1 | 9 | 2 | 100%
Create VHDX File | 7 | 1 | 10 | 1 | 100%
Finalize Project | 7 | 1 | 10 | 1 | 90%
Submit Project | 7 | 1 | 10 | 1 | 100%
Meetings/Attendance
| 2023-04-03 | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-04-12 | PERIODS 1: 2023-04-14
Andrew Pak | Present | Present | Present | Present | Present | PERIODS 1: Present
Corey Almonte | Present | Present | Present | Present | Present | PERIODS 1: Present
Annafi Islam | Present | Present | Present | Present | Present | PERIODS 1: Present
Harrison Yeung | Present | Present | Present | Present | Present | PERIODS 1: Present
Justin Spears | Present | Present | Present | Present | Present | PERIODS 1: Present
Team organized through a group chat where we planned meetings and assigned individual tasks to members in the group.
Delays due to difficulty of project and a new due date