## Group member 1
To-do list
To be completed by: |  | 2023-04-11 |  | Name: Andrew Pak
Deadline: |  | 2023-04-14 |  | Date: March 23, 2023
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-03-22 | 2023-03-31 | 2023-04-07 | 16 days | N/A
100% | Preparation | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1 day | N/A
100% | Group Planning/Tracking | 2023-03-23 | 2023-04-12 | 2023-04-14 | 22 days | Updated task assignment /new due date
100% | Create Group Database | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1 day | N/A
100% | Project2.Load_Data | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment/new due date
100% | Project2.Load_DimGender | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment/new due date
100% | Project2.Load_SalesManagers | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment/new due date
100% | Db Security authorization | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment /new due date
100% | PowerPoint Presentation | 2023-04-10 | 2023-04-12 | 2023-04-14 | 4 days | Updated task assignment/new due date
100% | Group Assigned Tasks | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | new due date
90% | Update Group Database | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | new due date
100% | Voice Annotations | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | new due date
90% | Finalize all tasks | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 days | new due date
100% | Submit all work | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 days | new due date

## Group member 2
To-do list
To be completed by: |  | 2023-04-11 |  | Name: Corey Almonte
Deadline: |  | 2023-04-14 |  | Date: March 23, 2023
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-03-22 | 2023-03-31 | 2023-04-07 | 16 days | N/A
100% | Preparation | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1 day | N/A
100% | Project2.Load_DimProduct | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment / new due date
100% | Project2.Load_DimProductCategory | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment/new due date
100% | Project2.Load_DimProduct Subcategory | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | Updated task assignment /new due date
100% | Group Assigned Tasks | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 day | N/A
100% | PowerPoint Presentation | 2023-04-10 | 2023-04-12 | 2023-04-14 | 4 days | Updated task assignment/new due date
100% | Update Group Database | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | New due date
100% | JDBC | 2023-04-10 | 2023-04-12 | 2023-04-14 | 4 days | N/A
100% | Voice Annotations | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | New due date
100% | Finalize all tasks | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date
100% | Submit all work | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date

## Group member 3
To-do list
To be completed by: |  | 2023-04-11 |  | Name: Justin Spears
Deadline: |  | 2023-04-14 |  | Date: March 23, 2023
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-03-22 | 2023-03-31 | 2023-04-07 | 16 days | N/A
100% | Preparation | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1 day | N/A
100% | Group Planning/Tracking | 2023-03-23 | 2023-04-12 | 2023-04-14 | 22 days | Updated task assignment /new due date
100% | CH01-01-Dimension.DimMaritalStatus | 2023-04-07 | 2023-04-10 | 2023-04-14 | 4 days | Updated task assignment /new due date
100% | CH01-01-Dimension.DimOccupation | 2023-04-07 | 2023-04-10 | 2023-04-14 | 4 days | Updated task assignment / new due date
100% | Project2.Add_ForeignKeysToStarSchema | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | New due date
100% | Project2.Drop_ForeignKeysFromStarSchema | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | New due date
100% | Project2.Load_StarSchemaData | 2023-04-07 | 2023-04-10 | 2023-04-14 | 7 days | New due date
100% | Group Assigned Tasks | 2023-04-10 | 2023-04-10 | 2023-04-14 | 1 day | New due date
100% | PowerPoint Presentation | 2023-04-10 | 2023-04-12 | 2023-04-14 | 2 days | Updated task assignment / new due date
100% | Update Group Database | 2023-04-10 | 2023-04-10 | 2023-04-14 | days | New due date
100% | Voice Annotations | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | New due date
100% | Finalize all tasks | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date
100% | Submit all work | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date

## Group member 4
To-do list
To be completed by: |  | 2023-04-11 |  | Name: Harrison Yeung
Deadline: |  | 2023-04-14 |  | Date: March 23, 2023
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-03-22 | 2023-03-31 | 2023-04-07 | 16 days | N/A
100% | Preparation | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1 day | N/A
100% | Project2.Load_DimCustomer | 2023-04-07 | 2023-04-10 | 2023-04-11 | 4 days | Updated task assignment /new due date
100% | Group Assigned Tasks | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | N/A
100% | PowerPoint Presentation | 2023-04-10 | 2023-04-12 | 2023-04-14 | 4 days | Updated task assignment / new due date
100% | Update Group Database | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | New due date
100% | Voice Annotations | 2023-04-10 | 2023-04-10 | 2012-04-14 | 4 days | New due date
100% | Finalize all tasks | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date
100% | Submit all work | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date

## Group member 5
To-do list
To be completed by: |  | 2023-04-11 |  | Name: Annafi Islam
Deadline: |  | 2023-04-14 |  | Date: March 23, 2023
Project 2
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-03-22 | 2023-03-31 | 2023-04-07 | 16 days | N/A
100% | Preparation | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1 day | N/A
100% | Project2.Load_DimOrderDate | 2023-04-07 | 2023-04-10 | 2023-04-14 | 4 days | Updated task assignment /new due date
100% | Group Assigned Tasks | 2023-04-10 | 2023-04-10 | 2023-04-14 | 14day | N/A
100% | PowerPoint Presentation | 2023-04-10 | 2023-04-12 | 2023-04-14 | 4 days | Updated task assignment / new due date
100% | Update Group Database | 2023-04-10 | 2023-04-10 | 2023-04-14 | 4 days | New due date
100% | Voice Annotations | 2023-04-10 | 2023-04-10 | 2012-04-14 | 4 days | New due date
100% | Finalize all tasks | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date
100% | Submit all work | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2 day | New due date